## Master Template
| Washington Ln |  |  | 2021-02-23
JOB NAME:____________________ |  |  | JOB NUMBER:__________________
| Trade | Estimate | Budget | Forecasted Cost | Cost to budget | Cost to Date | SUB #1 | Bid #1 | SUB #2 | Bid #2 | SUB #3 | Bid #3 | Harper Projected | Harper Cost | CNB Draw | Amount | Cash Available from Sale of House at $75,000
LND | Land | 40181.65 | 28127.155 | 60000 | -31872.845
CLS | Closing Costs | 2000 | 1800 | 700 | 1100
PLT | Platting/OSSF | 2000 | 1600 | 1135 | 465
DIRT | Land Clearing | 3000 | 1800 | 2100 | -300
ROAD | Gravel Road/Driveway | 9000 | 7200 |  | 7200
PLANS | House Plans | 1500 | 1200 | 2200 | -1000
WTR | Water Meter | 3000 | 2400 | 2600 | -200
APP | Appliances | 5000 | 4000 | 5770 | -1770
CAB | Cabinetry/Countertop | 13000 | 10400 | 15000 | -4600
CLN | Cleaning | 1500 | 750 |  | 750
CNC | Concrete | 36300 | 29040 | 39104 | -10064
CON | Contents | 0 | 0 | 0 | 0
SEP | Septic | 9000 | 4500 | 9500 | -5000
INT DOR | Doors | 2500 | 1750 | 4000 | -2250
GAR | Garage Door | 2500 | 1750 |  | 1750
EXT DOR | Doors | 4500 | 3150 | 3115 | 35
DRY | Drywall | 11520 | 8064 | 11000 | -2936
ELE | Electrical | 11000 | 8800 | 11000 | -2200
EQU | Equipment | 0 | 0 | 2000 | -2000
FCC | Floors - All (55/45) | 10000 | 7500 | 14400 | -6900
FCR | Floors - Resilient | 0 | 0 | 0 | 0
FCS | Floors - Stone | 0 | 0 | 0 | 0
FCT | Floors- Tile | 0 | 0 | 0 | 0
FCV | Floors - Vinyl | 0 | 0 | 0 | 0
FCW | Floors - Wood | 0 | 0 | 0 | 0
FEE | Permits & Fees | 1000 | 1000 | 1000 | 0
FEN | Fencing | 0 | 0 | 0 | 0
FNC | Finish Carpentry | 10000 | 1288 | 8000 | -6712
FNH | Finish Hardware | 2500 | 1750 | 1700 | 50
FPL | Fireplaces | 2300 | 1840 | 4000 | -2160
FPS | Fire Protection Systems | 0 | 0 | 0 | 0
FRM | Framing/Rough Carp | 38808 | 27165.6 | 65302.61 | -38137.01
GLS | Glass, Glazing, Storefro | 0 | 0 | 0 | 0
HMR | Haz Mat | 0 | 0 | 0 | 0
HVC | Heat, Vent, & A/C | 9200 | 7360 | 9200 | -1840
INS | Insulation | 9000 | 7200 | 6515 | 685
LAB | Labor Only | 1570 | 942 | 1747.71 | -805.71
LIT | Light Fixtures | 4000 | 3200 | 3940 | -740
LND | Landscaping/Other | 2900 | 2030 | 2900 | -870
MAS | Masonry | 3000 | 2100 | 3000 | -900
MAN | Mantle/Bench | 2100 |  | 2100
MBL | Marble | 0 | 0 | 0 | 0
MPR | Moisture Protection | 0 | 0 | 0 | 0
MSD | Mirrors/Shower Doors | 2000 | 1600 | 3000 | -1400
ORI | Ornamental Iron | 0 | 0 | 0 | 0
OUTG | Outdoor Grill Area | 3000
PLA | Int Lath & Plaster | 0 | 0 | 0 | 0
PLM | Plumbing | 13000 | 10400 | 17850 | -7450
PLF | Plumbing Fixtures | 4000 | 3200 | 4152.51 | -952.51
PNL | Paneling | 0 | 0 | 0 | 0
PNT | Painting | 12000 | 8400 | 10000 | -1600
POL | Pools & Spas | 0 | 0 | 0 | 0
RFG | Roofing | 15000 | 12750 | 11000 | 1750
SCF | Scaffolding | 0 | 0 | 0 | 0
SDG | Siding | 0 | 0 | 0 | 0
SFG | Soffit, Facia, Gutter | 2500 | 1750 | 1585 | 165
SPE | Specialty Items | 0 | 0 | 0 | 0
STJ | Steel Joist Components | 0 | 0 | 0 | 0
STL | Steel Components | 0 | 0 | 0 | 0
STR | Stairs | 0 | 0 | 0 | 0
STU | Stucco & Ext Plaster | 0 | 0 | 0 | 0
TBA | Toilet & Bath Access | 0 | 0 | 0 | 0
TIL | Tile | 7000 | 5600 | 8000 | -2400
TMP | Temporary Repairs | 0 | 0 | 0 | 0
WDA | Windows - Aluminum | 0 | 0 | 0 | 0
WDP | Windows- Slid Patio | 0 | 0 | 0 | 0
WDR | Window Reglaze & Rep | 0 | 0 | 0 | 0
WDS | Windows - Skylights | 0 | 0 | 0 | 0
WDT | Window Treatment | 0 | 0 | 0 | 0
WDV | Windows - Vinyl | 4500 | 3600 | 10000 | -6400
WDW | Window - Wood | 0 | 0 | 0 | 0
WPR | Wallpaper | 0 | 0 |  | 0
WTR | Water Restoration | 0 | 0 | 0 | 0
Residential Sales Tax |  | 0 | 0 | 0 | 0
Contents/Mitigation/Other |  | 0 | 0 | 0 | 0
| Subtotal | 316879.65 | 198879.6 | 358616.83 | -97637.23 | 0 | [6 empty] | 0 | 0
| O&P | 0 | 118000.05 | Profit | -358616.83
| Subtotal | 316879.65
| Other | 0
| Job Total | 0
|  | Projected Profit | 0% | Actual Profit | 0%
Job Total Less 5% to be Entered in JDE until Job is Complete |  |  |  |  | 0
GM Approval
Date
RESIDENTIAL (Tax after OP)